## Build Tracker
Phase | Task | Owner | Status | Start | End | Dependencies | Notes
Phase 0 | Set up Supabase project (auth, DB, storage) | Cameron | Complete | Week 1 | Week 1 |  | Schema deployed 3/23. 6 tables + RLS + storage bucket live.
Phase 0 | Scaffold Next.js + React + TypeScript project | Claude | Complete | Week 1 | Week 1 |  | Next.js App Router, Tailwind v4, done 3/23
Phase 0 | Design DB schema (users, campaigns, creatives, assets) | Claude | Complete | Week 1 | Week 2 |  | supabase-schema.sql created with 6 tables + RLS
Phase 0 | Integrate Perplexity Sonar API proxy endpoint | Claude | Complete | Week 2 | Week 2 | Supabase project | src/app/api/research/route.ts built
Phase 0 | Run 5-10 Perplexity test queries across verticals | Cameron | Not Started | Week 1 | Week 1 | API key + Supabase | DTC, gaming, fitness verticals
Phase 0 | Define exact export format spec (PNG + JSON schema) | D + Cameron | Complete | Week 1 | Week 1 |  | Confirmed: PNG + JSON config ZIP bundle
Phase 0 | Add real API keys to .env.local | Cameron | Complete |  |  |  | All 4 keys populated in creative-studio/.env.local
Phase 0 | Run Supabase schema SQL in Supabase SQL Editor | Cameron | Complete |  |  | Supabase project created | Executed successfully 3/23
Phase 1 | Build campaign creation wizard UI (4-step with brief) | Claude | Complete | Week 3 | Week 3 | Phase 0 complete | 4-step wizard: Basics, Audience, Campaign Brief, Review
Phase 1 | Build Perplexity query construction logic | Claude | Complete | Week 3 | Week 4 | API proxy | Reddit + YouTube source filtering, logic guide written
Phase 1 | Build research report UI (structured output + sentiment) | Claude | Complete | Week 4 | Week 4 | Query logic | Pain points, prizes, copy, per-topic sentiment with quotes, source badges
Phase 1 | Add insight selection flow (pick/modify before creating) | Claude | Complete | Week 4 | Week 4 | Report UI | Checkboxes, toggle chips, selected summary panel
Phase 2 | Evaluate Fabric.js vs. Konva.js | Claude | Complete | Week 1 | Week 2 |  | Fabric.js v6 selected: built-in JSON serialization, PNG export
Phase 2 | Build canvas editor core (drag-and-drop, layers) | Claude | Complete | Week 5 | Week 6 | Canvas lib chosen | Full Fabric.js editor with layer controls
Phase 2 | Create banner state templates (scratch, win, lose, brand) | Claude | Complete | Week 6 | Week 7 | Editor core | 4 tabs with independent canvas JSON state
Phase 2 | Build format templates (all IAB standard + custom dimensions) | Claude | Complete | Week 7 | Week 8 | Editor core | 10 IAB formats + custom WxH in types/index.ts
Phase 2 | Asset upload (logos, images) to Supabase Storage | Claude | Complete | Week 7 | Week 8 | Supabase Storage | Logo + background image upload to Supabase
Phase 2 | Customization controls (colors, fonts, CTA copy, prizes) | Claude | Complete | Week 7 | Week 8 | Templates | Color pickers, font dropdown, text inputs, font size slider
Phase 3 | Integrate Google Nano Banana API (proxy endpoint + auth) | Claude | Complete | Week 9 | Week 9 | Editor complete | src/app/api/generate/route.ts built
Phase 3 | Build prompt construction engine (research + brand assets to image prompts) | Claude | Complete | Week 9 | Week 10 | Nano Banana API | Logic guide written, lib/nanoBanana.ts created
Phase 3 | Generate A/B creative variations via Nano Banana | Claude | Complete | Week 10 | Week 10 | Prompt engine | Variations page at /campaign/[id]/variations
Phase 3 | Build side-by-side comparison grid UI | Claude | Complete | Week 10 | Week 10 | Nano Banana generation | Comparison grid with select toggle + regenerate
Phase 4 | PNG/SVG export from canvas | Claude | Complete | Week 11 | Week 11 | Editor + variations | Fabric.js toDataURL, offscreen canvas rendering
Phase 4 | JSON config generation | Claude | Complete | Week 11 | Week 11 | Export spec defined | Full config.json with campaign/creative/state structure
Phase 4 | ZIP bundle packaging (images + config) | Claude | Complete | Week 11 | Week 12 | PNG + JSON | Export page at /campaign/[id]/export using JSZip
Phase 4 | Build Creative Library page (/creatives) | Claude | Complete | Week 12 | Week 12 |  | Cross-campaign gallery with filters, previews, re-download
Phase 4 | Custom font upload in editor (.ttf/.woff2/.otf) | Claude | Complete | Week 12 | Week 12 | Editor core | FontFace API + Supabase Storage, upload in sidebar
Phase 4 | UX polish: shape dropdown, keyboard shortcuts, loading states | Claude | Complete | Week 12 | Week 12 |  | Delete key shortcut, fixed shape menu, loading/empty states
Phase 4 | Final UX polish, bug fixes, edge cases | D + Cameron | Not Started | Week 12 | Week 12
Phase 5 | Recruit 3-5 beta advertiser testers | Cameron | Not Started | Week 1 | Week 8 |  | From existing SkratchAds pipeline
Phase 5 | Beta launch to early testers | D + Cameron | Not Started | Week 13 | Week 13 | Phase 4 complete | Collect feedback, iterate
Phase 5 | Collect feedback, prioritize V2 backlog | Cameron | Not Started | Week 13 | Week 14 | Beta launch

## Open Questions
# | Question | Status | Decision | Date Resolved
1 | Should Creative Studio be free for all SkratchAds advertisers, or have its own pricing tier? | Resolved | Free, but requires account setup with validation | 2026-03-23
2 | What is the exact export format D needs? (PNG + JSON assumed) | Resolved | PNG + JSON config confirmed | 2026-03-23
3 | Custom fonts in V1, or lock to 10-15 curated web-safe fonts? | Resolved | V1 supports custom fonts | 2026-03-23
4 | Win probability config: set in Creative Studio or campaign manager? | Resolved | Handled in SkratchAds campaign manager, not Creative Studio | 2026-03-23
5 | Supabase vs. AWS for backend? | Resolved | Supabase confirmed | 2026-03-23

## Timeline
Phase | Milestone | Weeks | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
0 | Foundation | 1-2 | Complete
1 | Research Module | 3-4 | Complete
2 | Banner Editor | 5-8 | Complete
3 | Nano Banana A/B Gen | 9-10 | Complete
4 | Export + Polish | 11-12 | Complete
5 | Beta Launch | 13+ | Not Started